## PM_General Responsibilites
Project Management Responsibilities
Tasks | Contractor Name | NRVECRA | Notes
Designate Contractor project manager, system engineer, site manager, training manager, field service manager and provide contact information within fifteen (15) days of contract award | X
Approve Contractor project manager |  | X
Approve Contractor system engineer |  | X
Direct the project team’s personnel and subcontractors and assist in resolving project issues | X
Establish project communications protocol and maintain transmittal log | X
Establish and maintain a master project schedule for the design, implementation and acceptance of the system. | X
Provide schedule updates with each monthly status report, or more frequently as needed, to address changing circumstances. | X
Conduct monthly on-site project review meetings, or more often as needed, to address specific issues. | X
Conduct monthly project teleconferences, including, as needed, Web-based meeting spaces, between scheduled project review meetings, or more often as needed to address specific issues. | X
Develop and maintain risk/issue assessment, tracking, resolution, escalation and closeout | X
Develop change orders and present to NRVECRA for written approval prior to work commencing | X
Review and approve/deny change order, in writing (within 10 days of receipt) |  | X
Submit invoices based upon contract payment schedule with all supporting detailed information to include current project status report and current project schedule. | X
Review and approve or submit deficiencies for invoices within 10 days of receipt. |  | X
General Project Responsibilities
Tasks | Contractor Name | NRVECRA | Notes
Notify the NRVECRA of Contractor's intent to procure subcontractor(s) to perform tasks and/or provide equipment on the project. | X
Provide a list of proposed subcontractor(s), the tasks that they will perform and/or equipment that they will provide, and project references | X
Aprove qualifications of proposed subcontractors and key personnel. |  | X
Provide the NRVECRA information on its subcontractors’ personnel for the sake of criminal background checks and the issuance of temporary identification cards. | X
Schedule and provide site knowledgeable person to answer Contractor site questions on site surveys |  | X
Conduct site survey(s) and provide recommendations | X
Perform tower mapping and structural analyses | X
Develop required drawings | X
Develop network plans and IP backhaul requirements | X
Develop tower antenna placement plans | X
Develop frequency plans | X
Develop coverage maps | X
Develop site electrical loads | X
Develop preliminary cutover plan | X
Develop formal project schedule | X
Prepare acceptance test procedure (ATP) documents | X
Prepare one set of FCC license applications for NRVECRA’s submission & pay 1st time coordination fees | X
Sign and submit FCC license applications |  | X
If required, prepare additional FCC license applications and pay coordination fees | X
Prepare and submit one set of NRAO coordination applications on behalf of NRVECRA for P25 LMR frequencies and Microwave frequencies | X
Acquire property for any new greenfield sites (if required) |  | X
Coordinate with site ower to support site lease efforts | X
Furnish site owner accepted technical documents to support site lease efforts | X
Execute site lease for any non-customer-owned sites (if required) |  | X
Perform RF antenna sweep on existing transmission lines and antennas that will be reused | X
Contract Design Review (CDR) Meeting
Tasks | Contractor Name | NRVECRA | Notes
Conduct the Contract Design Reivew Meeting at a location provided by the NRVECRA with the NRVECRA project team members within thirty(30) days after contract signing or other customer notification to proceed | X
Assemble project team and travel to the NRVECRA location | X
Assemble NRVECRA project team for Contract Design Meeting |  | X
Present Baseline Project Schedule | X
Present preliminary information on sites and system design | X
Provide information on status of sites, frequencies, etc. | X

## DDR
Detailed Design Review (DDR) Deliverables
Tasks | Contractor Name | NRVECRA | Notes
Detailed Project Schedule | X
Radio System Technical Design
System Configuration - system overview & interoperability block diagrams | X
List of System Operations – Features & Functions | X
Coverage prediction maps | X
Traffic Loading Analysis | X
Frequency and Combiner plans | X
Identify FCC licensed frequencies that meet contour limits and fulfill the frequency plan | X
Alarm System Plan | X
System Control and Management | X
Failure / Bypass Modes | X
List of deliverable equipment for each site | X
Network connection plan and backhaul requirements | X
Site Design
Site Plans
Site plot drawings | X
Site Access | X
Site Grounding | X
Tower Elevation and Plans
Tower Structural Analysis | X
Antenna placement drawings | X
Building / Shelter Plans
Shelter floor plan and dimension drawings | X
Equipment Rack elevation drawings | X
Electrical System Design | X
AC power and BTU requirements | X
UPS and / or DC Power System | X
Generator | X
Grounding and Surge Protection | X
HVAC | X
Fire detection / suppression | X
Connectivity Network
Network Topology Diagrams | X
Path Survey Reports | X
Fiber Optic Maps | X
MW Frequency Plan | X
Interfaces | X
Dispatch Center
Dispatch Center Block Diagram, including backup radios | X
Console Configuration Plan | X
Logging Recorder Connectivity Plan | X
CAD Integration Plan (If required) | X
Draft Acceptance Test Plans
Radio Staging | X
Microwave/Connectivity Network Staging | X
Radio System (Field Test) | X
Microwave/Connectivity Network (Field Test) | X
Coverage (Field Drive Test) | X
30 day Operational Test | X
Cutover | X
Subscribers | X
Plan for Fleet Mapping | X
Training Plans | X
Provide all DDR deliverables for review (15 days prior to DDR) | X
DDR Review Meeting | X | X
Review DDR documents |  | X
Conduct the DDR no more than 150 days after contract execution | X
Provide comments from the design following DDR meeting (within 10 days) |  | X
Revise DDR documents (within 15 days) | X
Approve DDR documents (within 10 days) |  | X

## General Site Responsibilities
General Site Responsibilities
Tasks | Contractor Name | NRVECRA | Notes
Coordinate with federal, state, and local government agencies, as required | X
Provide access to necessary buildings and sites, including temporary ID badges for Contractor, if needed. |  | X
Provide parking permits for Contractor project team for any restricted parking areas |  | X
Provide adequate road access for delivery vehicles | X
Provide temporary parking to off-load equipment at all buildings and sites |  | X
Clean up site and remove all installation debris | X
Remove any hazardous material found on site (to the extent the hazardous material is not generated by Vendor/Contractor) |  | X
If required, coordinate with the utility company to provide appropriate utility transformer additions or upgrades required to provide the adequate AC power needed for each site | X
Provide reasonable remediation for adequate AC utility connection | X
Comply with FCC OET65 Signage requirements(https://www.fcc.gov/general/oet-bulletins-line) for any new tower construction. | X
Develop sites and install materials in accordance with industry and Vendor standards | X

## Site 1
Site 1 - (Insert Site Name)
Site Tasks | Contractor Name | NRVECRA | Notes
Complete one set of forms/applications to support zoning permits and approval for site changes | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Perform physical path surveys for each microwave path (microwave path studies are not final until a physical survey is made) | X
Provide existing site plans (if available) |  | X
Conduct grounding inspection and provide recommendations | X
Conduct site survey(s) and provide recommendations | X
Tower Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for tower (if new tower) | X
Grade land, construct silt fences, and remove weeds and brush | X
After assurances have been made that this site can be developed, develop site plot drawings of compound showing new tower, shelter, generator, and fuel tank locations | X
Perform geotechnical investigation for tower leg foundations in accordance with TIA-222 standards for new towers, and review results with at DDR | X
If geotechnical investigation results indicate a foundation design is required to address other than typical soil conditions. Submit a site-specific foundation design, and pricing change request, at, or prior too, DDR | X
Prepare new tower NEPA/SHPO environmental studies and THPO filings | X
Prepare and submit construction permits for new tower | X
Prepare and submit electrical permits | X
Identify specific tower attachment points to mount new antennas per the system design | X
Confirm availability of tower attachment points for proposed antennas | X
Perform tower mapping and structural analysis on existing tower and provide results at DDR. If tower fails load analysis, Contractor will provide quotes to strengthen tower (if possible), replace the tower, or provide site acquisition services. | X
Strengthen or replace tower (if required by structural analysis results) at an agreed upon additional cost and schedule adjustment | X
Provide space on existing tower to mount new system antennas at Contractor specified locations as part of the site lease(s) |  | X
Provide adequate space on cable ice bridge, and tower cable ladders, to support new cable runs | X
Install new antenna(s) using appropriate side arms and mounting hardware | X
Install antenna coax, connectors and jumpers, using cable clamps to properly secure cable to tower, and add grounding kits at the top, bottom, and on ice bridge | X
Install new tower top amplifiers for the P25 radio system | X
Install antenna lightning protection devices on each transmission line LMR run after it enters shelter via cable entry port; ground device to main ground bus bars | X
If required, install new microwave dish(es), on pipe mounts with anti-sway kits | X
Install ice shields over microwave dishes if not at the top of tower | X
Install new microwave waveguide or coaxial feed lines, secure to cable ladder(s), and add grounding kits at the top, bottom, and on ice bridge | X
Tag and identify each new antenna line | X
Sweep test each new antenna line in accordance with Contractor's “Transmission Line Analysis (Antenna Sweep) procedure | X
Shelter Tasks | Contractor Name | NRVECRA | Notes
Provide and install new shelter | X
Grade land, construct silt fences, and remove weeds and brush | X
Provide floor space in existing RF shelter for new equipment racks and DC battery plant or UPS used in the new design |  | X
Provide adequate shelter/equipment room utility AC electrical power, single-point ground system, and HVAC | X
Provide new cable entry port(s) if required | X
Upgrade existing interior ground system | X
Provide additional cable ladder for new equipment row | X
If needed, prepare and submit electrical permits on behalf of the customer | X
Install new DC power plant or UPS and wire to racks | X
Provide demarcation blocks for connection to existing legacy radios to be used in interoperability system | X
Connect site alarms to alarm punchblock (i.e smoke detector, generator, ATS, Temperature, etc.) | X
Generator Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for new generator pad (and fuel tank pad if necessary) | X
Have an architectural firm develop site compound plot drawings of compound showing tower, shelter, new generator (and fuel tank if necessary) | X
Complete one set of forms/applications to support zoning permits and approvals | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Prepare and submit construction permits for new generator (and fuel tank if necessary) | X
Prepare and submit electrical permits | X
Grade land, construct silt fences, and remove weeds and brush | X
Construct/pour generator pads (and fuel tank pad if necessary) | X
Transport, off-load, and set new generator on pad (and fuel tank if necessary) | X
Install ATS | X
Trench in generator electrical service and control circuits to shelter-mounted ATS | X
Ground generator (and fuel tank if necessary) to tower/shelter ground system | X
Fill generator fuel tank (first fill) | X
Provide factory generator technician for first-start service | X

## Site 2
Site 2 - (Insert Site Name)
Site Tasks | Contractor Name | NRVECRA | Notes
Complete one set of forms/applications to support zoning permits and approval for site changes | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Perform physical path surveys for each microwave path (microwave path studies are not final until a physical survey is made) | X
Provide existing site plans (if available) |  | X
Conduct grounding inspection and provide recommendations | X
Conduct site survey(s) and provide recommendations | X
Tower Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for tower (if new tower) | X
Grade land, construct silt fences, and remove weeds and brush | X
After assurances have been made that this site can be developed, develop site plot drawings of compound showing new tower, shelter, generator, and fuel tank locations | X
Perform geotechnical investigation for tower leg foundations in accordance with TIA-222 standards for new towers, and review results with at DDR | X
If geotechnical investigation results indicate a foundation design is required to address other than typical soil conditions. Submit a site-specific foundation design, and pricing change request, at, or prior too, DDR | X
Prepare new tower NEPA/SHPO environmental studies and THPO filings | X
Prepare and submit construction permits for new tower | X
Prepare and submit electrical permits | X
Identify specific tower attachment points to mount new antennas per the system design | X
Confirm availability of tower attachment points for proposed antennas | X
Perform tower mapping and structural analysis on existing tower and provide results at DDR. If tower fails load analysis, Contractor will provide quotes to strengthen tower (if possible), replace the tower, or provide site acquisition services. | X
Strengthen or replace tower (if required by structural analysis results) at an agreed upon additional cost and schedule adjustment | X
Provide space on existing tower to mount new system antennas at Contractor specified locations as part of the site lease(s) |  | X
Provide adequate space on cable ice bridge, and tower cable ladders, to support new cable runs | X
Install new antenna(s) using appropriate side arms and mounting hardware | X
Install antenna coax, connectors and jumpers, using cable clamps to properly secure cable to tower, and add grounding kits at the top, bottom, and on ice bridge | X
Install new tower top amplifiers for the P25 radio system | X
Install antenna lightning protection devices on each transmission line LMR run after it enters shelter via cable entry port; ground device to main ground bus bars | X
If required, install new microwave dish(es), on pipe mounts with anti-sway kits | X
Install ice shields over microwave dishes if not at the top of tower | X
Install new microwave waveguide or coaxial feed lines, secure to cable ladder(s), and add grounding kits at the top, bottom, and on ice bridge | X
Tag and identify each new antenna line | X
Sweep test each new antenna line in accordance with Contractor's “Transmission Line Analysis (Antenna Sweep) procedure | X
Shelter Tasks | Contractor Name | NRVECRA | Notes
Provide and install new shelter | X
Grade land, construct silt fences, and remove weeds and brush | X
Provide floor space in existing RF shelter for new equipment racks and DC battery plant or UPS used in the new design |  | X
Provide adequate shelter/equipment room utility AC electrical power, single-point ground system, and HVAC | X
Provide new cable entry port(s) if required | X
Upgrade existing interior ground system | X
Provide additional cable ladder for new equipment row | X
If needed, prepare and submit electrical permits on behalf of the customer | X
Install new DC power plant or UPS and wire to racks | X
Provide demarcation blocks for connection to existing legacy radios to be used in interoperability system | X
Connect site alarms to alarm punchblock (i.e smoke detector, generator, ATS, Temperature, etc.) | X
Generator Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for new generator pad (and fuel tank pad if necessary) | X
Have an architectural firm develop site compound plot drawings of compound showing tower, shelter, new generator (and fuel tank if necessary) | X
Complete one set of forms/applications to support zoning permits and approvals | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Prepare and submit construction permits for new generator (and fuel tank if necessary) | X
Prepare and submit electrical permits | X
Grade land, construct silt fences, and remove weeds and brush | X
Construct/pour generator pads (and fuel tank pad if necessary) | X
Transport, off-load, and set new generator on pad (and fuel tank if necessary) | X
Install ATS | X
Trench in generator electrical service and control circuits to shelter-mounted ATS | X
Ground generator (and fuel tank if necessary) to tower/shelter ground system | X
Fill generator fuel tank (first fill) | X
Provide factory generator technician for first-start service | X

## Site 3
Site 3 - (Insert Site Name)
Site Tasks | Contractor Name | NRVECRA | Notes
Complete one set of forms/applications to support zoning permits and approval for site changes | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Perform physical path surveys for each microwave path (microwave path studies are not final until a physical survey is made) | X
Provide existing site plans (if available) |  | X
Conduct grounding inspection and provide recommendations | X
Conduct site survey(s) and provide recommendations | X
Tower Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for tower (if new tower) | X
Grade land, construct silt fences, and remove weeds and brush | X
After assurances have been made that this site can be developed, develop site plot drawings of compound showing new tower, shelter, generator, and fuel tank locations | X
Perform geotechnical investigation for tower leg foundations in accordance with TIA-222 standards for new towers, and review results with at DDR | X
If geotechnical investigation results indicate a foundation design is required to address other than typical soil conditions. Submit a site-specific foundation design, and pricing change request, at, or prior too, DDR | X
Prepare new tower NEPA/SHPO environmental studies and THPO filings | X
Prepare and submit construction permits for new tower | X
Prepare and submit electrical permits | X
Identify specific tower attachment points to mount new antennas per the system design | X
Confirm availability of tower attachment points for proposed antennas | X
Perform tower mapping and structural analysis on existing tower and provide results at DDR. If tower fails load analysis, Contractor will provide quotes to strengthen tower (if possible), replace the tower, or provide site acquisition services. | X
Strengthen or replace tower (if required by structural analysis results) at an agreed upon additional cost and schedule adjustment | X
Provide space on existing tower to mount new system antennas at Contractor specified locations as part of the site lease(s) |  | X
Provide adequate space on cable ice bridge, and tower cable ladders, to support new cable runs | X
Install new antenna(s) using appropriate side arms and mounting hardware | X
Install antenna coax, connectors and jumpers, using cable clamps to properly secure cable to tower, and add grounding kits at the top, bottom, and on ice bridge | X
Install new tower top amplifiers for the P25 radio system | X
Install antenna lightning protection devices on each transmission line LMR run after it enters shelter via cable entry port; ground device to main ground bus bars | X
If required, install new microwave dish(es), on pipe mounts with anti-sway kits | X
Install ice shields over microwave dishes if not at the top of tower | X
Install new microwave waveguide or coaxial feed lines, secure to cable ladder(s), and add grounding kits at the top, bottom, and on ice bridge | X
Tag and identify each new antenna line | X
Sweep test each new antenna line in accordance with Contractor's “Transmission Line Analysis (Antenna Sweep) procedure | X
Shelter Tasks | Contractor Name | NRVECRA | Notes
Provide and install new shelter | X
Grade land, construct silt fences, and remove weeds and brush | X
Provide floor space in existing RF shelter for new equipment racks and DC battery plant or UPS used in the new design |  | X
Provide adequate shelter/equipment room utility AC electrical power, single-point ground system, and HVAC | X
Provide new cable entry port(s) if required | X
Upgrade existing interior ground system | X
Provide additional cable ladder for new equipment row | X
If needed, prepare and submit electrical permits on behalf of the customer | X
Install new DC power plant or UPS and wire to racks | X
Provide demarcation blocks for connection to existing legacy radios to be used in interoperability system | X
Connect site alarms to alarm punchblock (i.e smoke detector, generator, ATS, Temperature, etc.) | X
Generator Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for new generator pad (and fuel tank pad if necessary) | X
Have an architectural firm develop site compound plot drawings of compound showing tower, shelter, new generator (and fuel tank if necessary) | X
Complete one set of forms/applications to support zoning permits and approvals | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Prepare and submit construction permits for new generator (and fuel tank if necessary) | X
Prepare and submit electrical permits | X
Grade land, construct silt fences, and remove weeds and brush | X
Construct/pour generator pads (and fuel tank pad if necessary) | X
Transport, off-load, and set new generator on pad (and fuel tank if necessary) | X
Install ATS | X
Trench in generator electrical service and control circuits to shelter-mounted ATS | X
Ground generator (and fuel tank if necessary) to tower/shelter ground system | X
Fill generator fuel tank (first fill) | X
Provide factory generator technician for first-start service | X

## Site 4
Site 4 - (Insert Site Name)
Site Tasks | Contractor Name | NRVECRA | Notes
Complete one set of forms/applications to support zoning permits and approval for site changes | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Perform physical path surveys for each microwave path (microwave path studies are not final until a physical survey is made) | X
Provide existing site plans (if available) |  | X
Conduct grounding inspection and provide recommendations | X
Conduct site survey(s) and provide recommendations | X
Tower Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for tower (if new tower) | X
Grade land, construct silt fences, and remove weeds and brush | X
After assurances have been made that this site can be developed, develop site plot drawings of compound showing new tower, shelter, generator, and fuel tank locations | X
Perform geotechnical investigation for tower leg foundations in accordance with TIA-222 standards for new towers, and review results with at DDR | X
If geotechnical investigation results indicate a foundation design is required to address other than typical soil conditions. Submit a site-specific foundation design, and pricing change request, at, or prior too, DDR | X
Prepare new tower NEPA/SHPO environmental studies and THPO filings | X
Prepare and submit construction permits for new tower | X
Prepare and submit electrical permits | X
Identify specific tower attachment points to mount new antennas per the system design | X
Confirm availability of tower attachment points for proposed antennas | X
Perform tower mapping and structural analysis on existing tower and provide results at DDR. If tower fails load analysis, Contractor will provide quotes to strengthen tower (if possible), replace the tower, or provide site acquisition services. | X
Strengthen or replace tower (if required by structural analysis results) at an agreed upon additional cost and schedule adjustment | X
Provide space on existing tower to mount new system antennas at Contractor specified locations as part of the site lease(s) |  | X
Provide adequate space on cable ice bridge, and tower cable ladders, to support new cable runs | X
Install new antenna(s) using appropriate side arms and mounting hardware | X
Install antenna coax, connectors and jumpers, using cable clamps to properly secure cable to tower, and add grounding kits at the top, bottom, and on ice bridge | X
Install new tower top amplifiers for the P25 radio system | X
Install antenna lightning protection devices on each transmission line LMR run after it enters shelter via cable entry port; ground device to main ground bus bars | X
If required, install new microwave dish(es), on pipe mounts with anti-sway kits | X
Install ice shields over microwave dishes if not at the top of tower | X
Install new microwave waveguide or coaxial feed lines, secure to cable ladder(s), and add grounding kits at the top, bottom, and on ice bridge | X
Tag and identify each new antenna line | X
Sweep test each new antenna line in accordance with Contractor's “Transmission Line Analysis (Antenna Sweep) procedure | X
Shelter Tasks | Contractor Name | NRVECRA | Notes
Provide and install new shelter | X
Grade land, construct silt fences, and remove weeds and brush | X
Provide floor space in existing RF shelter for new equipment racks and DC battery plant or UPS used in the new design |  | X
Provide adequate shelter/equipment room utility AC electrical power, single-point ground system, and HVAC | X
Provide new cable entry port(s) if required | X
Upgrade existing interior ground system | X
Provide additional cable ladder for new equipment row | X
If needed, prepare and submit electrical permits on behalf of the customer | X
Install new DC power plant or UPS and wire to racks | X
Provide demarcation blocks for connection to existing legacy radios to be used in interoperability system | X
Connect site alarms to alarm punchblock (i.e smoke detector, generator, ATS, Temperature, etc.) | X
Generator Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for new generator pad (and fuel tank pad if necessary) | X
Have an architectural firm develop site compound plot drawings of compound showing tower, shelter, new generator (and fuel tank if necessary) | X
Complete one set of forms/applications to support zoning permits and approvals | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Prepare and submit construction permits for new generator (and fuel tank if necessary) | X
Prepare and submit electrical permits | X
Grade land, construct silt fences, and remove weeds and brush | X
Construct/pour generator pads (and fuel tank pad if necessary) | X
Transport, off-load, and set new generator on pad (and fuel tank if necessary) | X
Install ATS | X
Trench in generator electrical service and control circuits to shelter-mounted ATS | X
Ground generator (and fuel tank if necessary) to tower/shelter ground system | X
Fill generator fuel tank (first fill) | X
Provide factory generator technician for first-start service | X

## Site 5
Site 5 - (Insert Site Name)
Site Tasks | Contractor Name | NRVECRA | Notes
Complete one set of forms/applications to support zoning permits and approval for site changes | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Perform physical path surveys for each microwave path (microwave path studies are not final until a physical survey is made) | X
Provide existing site plans (if available) |  | X
Conduct grounding inspection and provide recommendations | X
Conduct site survey(s) and provide recommendations | X
Tower Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for tower (if new tower) | X
Grade land, construct silt fences, and remove weeds and brush | X
After assurances have been made that this site can be developed, develop site plot drawings of compound showing new tower, shelter, generator, and fuel tank locations | X
Perform geotechnical investigation for tower leg foundations in accordance with TIA-222 standards for new towers, and review results with at DDR | X
If geotechnical investigation results indicate a foundation design is required to address other than typical soil conditions. Submit a site-specific foundation design, and pricing change request, at, or prior too, DDR | X
Prepare new tower NEPA/SHPO environmental studies and THPO filings | X
Prepare and submit construction permits for new tower | X
Prepare and submit electrical permits | X
Identify specific tower attachment points to mount new antennas per the system design | X
Confirm availability of tower attachment points for proposed antennas | X
Perform tower mapping and structural analysis on existing tower and provide results at DDR. If tower fails load analysis, Contractor will provide quotes to strengthen tower (if possible), replace the tower, or provide site acquisition services. | X
Strengthen or replace tower (if required by structural analysis results) at an agreed upon additional cost and schedule adjustment | X
Provide space on existing tower to mount new system antennas at Contractor specified locations as part of the site lease(s) |  | X
Provide adequate space on cable ice bridge, and tower cable ladders, to support new cable runs | X
Install new antenna(s) using appropriate side arms and mounting hardware | X
Install antenna coax, connectors and jumpers, using cable clamps to properly secure cable to tower, and add grounding kits at the top, bottom, and on ice bridge | X
Install new tower top amplifiers for the P25 radio system | X
Install antenna lightning protection devices on each transmission line LMR run after it enters shelter via cable entry port; ground device to main ground bus bars | X
If required, install new microwave dish(es), on pipe mounts with anti-sway kits | X
Install ice shields over microwave dishes if not at the top of tower | X
Install new microwave waveguide or coaxial feed lines, secure to cable ladder(s), and add grounding kits at the top, bottom, and on ice bridge | X
Tag and identify each new antenna line | X
Sweep test each new antenna line in accordance with Contractor's “Transmission Line Analysis (Antenna Sweep) procedure | X
Shelter Tasks | Contractor Name | NRVECRA | Notes
Provide and install new shelter | X
Grade land, construct silt fences, and remove weeds and brush | X
Provide floor space in existing RF shelter for new equipment racks and DC battery plant or UPS used in the new design |  | X
Provide adequate shelter/equipment room utility AC electrical power, single-point ground system, and HVAC | X
Provide new cable entry port(s) if required | X
Upgrade existing interior ground system | X
Provide additional cable ladder for new equipment row | X
If needed, prepare and submit electrical permits on behalf of the customer | X
Install new DC power plant or UPS and wire to racks | X
Provide demarcation blocks for connection to existing legacy radios to be used in interoperability system | X
Connect site alarms to alarm punchblock (i.e smoke detector, generator, ATS, Temperature, etc.) | X
Generator Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for new generator pad (and fuel tank pad if necessary) | X
Have an architectural firm develop site compound plot drawings of compound showing tower, shelter, new generator (and fuel tank if necessary) | X
Complete one set of forms/applications to support zoning permits and approvals | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Prepare and submit construction permits for new generator (and fuel tank if necessary) | X
Prepare and submit electrical permits | X
Grade land, construct silt fences, and remove weeds and brush | X
Construct/pour generator pads (and fuel tank pad if necessary) | X
Transport, off-load, and set new generator on pad (and fuel tank if necessary) | X
Install ATS | X
Trench in generator electrical service and control circuits to shelter-mounted ATS | X
Ground generator (and fuel tank if necessary) to tower/shelter ground system | X
Fill generator fuel tank (first fill) | X
Provide factory generator technician for first-start service | X

## Site 6
Site 6 - (Insert Site Name)
Site Tasks | Contractor Name | NRVECRA | Notes
Complete one set of forms/applications to support zoning permits and approval for site changes | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Perform physical path surveys for each microwave path (microwave path studies are not final until a physical survey is made) | X
Provide existing site plans (if available) |  | X
Conduct grounding inspection and provide recommendations | X
Conduct site survey(s) and provide recommendations | X
Tower Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for tower (if new tower) | X
Grade land, construct silt fences, and remove weeds and brush | X
After assurances have been made that this site can be developed, develop site plot drawings of compound showing new tower, shelter, generator, and fuel tank locations | X
Perform geotechnical investigation for tower leg foundations in accordance with TIA-222 standards for new towers, and review results with at DDR | X
If geotechnical investigation results indicate a foundation design is required to address other than typical soil conditions. Submit a site-specific foundation design, and pricing change request, at, or prior too, DDR | X
Prepare new tower NEPA/SHPO environmental studies and THPO filings | X
Prepare and submit construction permits for new tower | X
Prepare and submit electrical permits | X
Identify specific tower attachment points to mount new antennas per the system design | X
Confirm availability of tower attachment points for proposed antennas | X
Perform tower mapping and structural analysis on existing tower and provide results at DDR. If tower fails load analysis, Contractor will provide quotes to strengthen tower (if possible), replace the tower, or provide site acquisition services. | X
Strengthen or replace tower (if required by structural analysis results) at an agreed upon additional cost and schedule adjustment | X
Provide space on existing tower to mount new system antennas at Contractor specified locations as part of the site lease(s) |  | X
Provide adequate space on cable ice bridge, and tower cable ladders, to support new cable runs | X
Install new antenna(s) using appropriate side arms and mounting hardware | X
Install antenna coax, connectors and jumpers, using cable clamps to properly secure cable to tower, and add grounding kits at the top, bottom, and on ice bridge | X
Install new tower top amplifiers for the P25 radio system | X
Install antenna lightning protection devices on each transmission line LMR run after it enters shelter via cable entry port; ground device to main ground bus bars | X
If required, install new microwave dish(es), on pipe mounts with anti-sway kits | X
Install ice shields over microwave dishes if not at the top of tower | X
Install new microwave waveguide or coaxial feed lines, secure to cable ladder(s), and add grounding kits at the top, bottom, and on ice bridge | X
Tag and identify each new antenna line | X
Sweep test each new antenna line in accordance with Contractor's “Transmission Line Analysis (Antenna Sweep) procedure | X
Shelter Tasks | Contractor Name | NRVECRA | Notes
Provide and install new shelter | X
Grade land, construct silt fences, and remove weeds and brush | X
Provide floor space in existing RF shelter for new equipment racks and DC battery plant or UPS used in the new design |  | X
Provide adequate shelter/equipment room utility AC electrical power, single-point ground system, and HVAC | X
Provide new cable entry port(s) if required | X
Upgrade existing interior ground system | X
Provide additional cable ladder for new equipment row | X
If needed, prepare and submit electrical permits on behalf of the customer | X
Install new DC power plant or UPS and wire to racks | X
Provide demarcation blocks for connection to existing legacy radios to be used in interoperability system | X
Connect site alarms to alarm punchblock (i.e smoke detector, generator, ATS, Temperature, etc.) | X
Generator Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for new generator pad (and fuel tank pad if necessary) | X
Have an architectural firm develop site compound plot drawings of compound showing tower, shelter, new generator (and fuel tank if necessary) | X
Complete one set of forms/applications to support zoning permits and approvals | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Prepare and submit construction permits for new generator (and fuel tank if necessary) | X
Prepare and submit electrical permits | X
Grade land, construct silt fences, and remove weeds and brush | X
Construct/pour generator pads (and fuel tank pad if necessary) | X
Transport, off-load, and set new generator on pad (and fuel tank if necessary) | X
Install ATS | X
Trench in generator electrical service and control circuits to shelter-mounted ATS | X
Ground generator (and fuel tank if necessary) to tower/shelter ground system | X
Fill generator fuel tank (first fill) | X
Provide factory generator technician for first-start service | X

## Site 7
Site 7 - (Insert Site Name)
Site Tasks | Contractor Name | NRVECRA | Notes
Complete one set of forms/applications to support zoning permits and approval for site changes | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Perform physical path surveys for each microwave path (microwave path studies are not final until a physical survey is made) | X
Provide existing site plans (if available) |  | X
Conduct grounding inspection and provide recommendations | X
Conduct site survey(s) and provide recommendations | X
Tower Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for tower (if new tower) | X
Grade land, construct silt fences, and remove weeds and brush | X
After assurances have been made that this site can be developed, develop site plot drawings of compound showing new tower, shelter, generator, and fuel tank locations | X
Perform geotechnical investigation for tower leg foundations in accordance with TIA-222 standards for new towers, and review results with at DDR | X
If geotechnical investigation results indicate a foundation design is required to address other than typical soil conditions. Submit a site-specific foundation design, and pricing change request, at, or prior too, DDR | X
Prepare new tower NEPA/SHPO environmental studies and THPO filings | X
Prepare and submit construction permits for new tower | X
Prepare and submit electrical permits | X
Identify specific tower attachment points to mount new antennas per the system design | X
Confirm availability of tower attachment points for proposed antennas | X
Perform tower mapping and structural analysis on existing tower and provide results at DDR. If tower fails load analysis, Contractor will provide quotes to strengthen tower (if possible), replace the tower, or provide site acquisition services. | X
Strengthen or replace tower (if required by structural analysis results) at an agreed upon additional cost and schedule adjustment | X
Provide space on existing tower to mount new system antennas at Contractor specified locations as part of the site lease(s) |  | X
Provide adequate space on cable ice bridge, and tower cable ladders, to support new cable runs | X
Install new antenna(s) using appropriate side arms and mounting hardware | X
Install antenna coax, connectors and jumpers, using cable clamps to properly secure cable to tower, and add grounding kits at the top, bottom, and on ice bridge | X
Install new tower top amplifiers for the P25 radio system | X
Install antenna lightning protection devices on each transmission line LMR run after it enters shelter via cable entry port; ground device to main ground bus bars | X
If required, install new microwave dish(es), on pipe mounts with anti-sway kits | X
Install ice shields over microwave dishes if not at the top of tower | X
Install new microwave waveguide or coaxial feed lines, secure to cable ladder(s), and add grounding kits at the top, bottom, and on ice bridge | X
Tag and identify each new antenna line | X
Sweep test each new antenna line in accordance with Contractor's “Transmission Line Analysis (Antenna Sweep) procedure | X
Shelter Tasks | Contractor Name | NRVECRA | Notes
Provide and install new shelter | X
Grade land, construct silt fences, and remove weeds and brush | X
Provide floor space in existing RF shelter for new equipment racks and DC battery plant or UPS used in the new design |  | X
Provide adequate shelter/equipment room utility AC electrical power, single-point ground system, and HVAC | X
Provide new cable entry port(s) if required | X
Upgrade existing interior ground system | X
Provide additional cable ladder for new equipment row | X
If needed, prepare and submit electrical permits on behalf of the customer | X
Install new DC power plant or UPS and wire to racks | X
Provide demarcation blocks for connection to existing legacy radios to be used in interoperability system | X
Connect site alarms to alarm punchblock (i.e smoke detector, generator, ATS, Temperature, etc.) | X
Generator Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for new generator pad (and fuel tank pad if necessary) | X
Have an architectural firm develop site compound plot drawings of compound showing tower, shelter, new generator (and fuel tank if necessary) | X
Complete one set of forms/applications to support zoning permits and approvals | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Prepare and submit construction permits for new generator (and fuel tank if necessary) | X
Prepare and submit electrical permits | X
Grade land, construct silt fences, and remove weeds and brush | X
Construct/pour generator pads (and fuel tank pad if necessary) | X
Transport, off-load, and set new generator on pad (and fuel tank if necessary) | X
Install ATS | X
Trench in generator electrical service and control circuits to shelter-mounted ATS | X
Ground generator (and fuel tank if necessary) to tower/shelter ground system | X
Fill generator fuel tank (first fill) | X
Provide factory generator technician for first-start service | X

## Site 8
Site 8 - (Insert Site Name)
Site Tasks | Contractor Name | NRVECRA | Notes
Complete one set of forms/applications to support zoning permits and approval for site changes | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Perform physical path surveys for each microwave path (microwave path studies are not final until a physical survey is made) | X
Provide existing site plans (if available) |  | X
Conduct grounding inspection and provide recommendations | X
Conduct site survey(s) and provide recommendations | X
Tower Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for tower (if new tower) | X
Grade land, construct silt fences, and remove weeds and brush | X
After assurances have been made that this site can be developed, develop site plot drawings of compound showing new tower, shelter, generator, and fuel tank locations | X
Perform geotechnical investigation for tower leg foundations in accordance with TIA-222 standards for new towers, and review results with at DDR | X
If geotechnical investigation results indicate a foundation design is required to address other than typical soil conditions. Submit a site-specific foundation design, and pricing change request, at, or prior too, DDR | X
Prepare new tower NEPA/SHPO environmental studies and THPO filings | X
Prepare and submit construction permits for new tower | X
Prepare and submit electrical permits | X
Identify specific tower attachment points to mount new antennas per the system design | X
Confirm availability of tower attachment points for proposed antennas | X
Perform tower mapping and structural analysis on existing tower and provide results at DDR. If tower fails load analysis, Contractor will provide quotes to strengthen tower (if possible), replace the tower, or provide site acquisition services. | X
Strengthen or replace tower (if required by structural analysis results) at an agreed upon additional cost and schedule adjustment | X
Provide space on existing tower to mount new system antennas at Contractor specified locations as part of the site lease(s) |  | X
Provide adequate space on cable ice bridge, and tower cable ladders, to support new cable runs | X
Install new antenna(s) using appropriate side arms and mounting hardware | X
Install antenna coax, connectors and jumpers, using cable clamps to properly secure cable to tower, and add grounding kits at the top, bottom, and on ice bridge | X
Install new tower top amplifiers for the P25 radio system | X
Install antenna lightning protection devices on each transmission line LMR run after it enters shelter via cable entry port; ground device to main ground bus bars | X
If required, install new microwave dish(es), on pipe mounts with anti-sway kits | X
Install ice shields over microwave dishes if not at the top of tower | X
Install new microwave waveguide or coaxial feed lines, secure to cable ladder(s), and add grounding kits at the top, bottom, and on ice bridge | X
Tag and identify each new antenna line | X
Sweep test each new antenna line in accordance with Contractor's “Transmission Line Analysis (Antenna Sweep) procedure | X
Shelter Tasks | Contractor Name | NRVECRA | Notes
Provide and install new shelter | X
Grade land, construct silt fences, and remove weeds and brush | X
Provide floor space in existing RF shelter for new equipment racks and DC battery plant or UPS used in the new design |  | X
Provide adequate shelter/equipment room utility AC electrical power, single-point ground system, and HVAC | X
Provide new cable entry port(s) if required | X
Upgrade existing interior ground system | X
Provide additional cable ladder for new equipment row | X
If needed, prepare and submit electrical permits on behalf of the customer | X
Install new DC power plant or UPS and wire to racks | X
Provide demarcation blocks for connection to existing legacy radios to be used in interoperability system | X
Connect site alarms to alarm punchblock (i.e smoke detector, generator, ATS, Temperature, etc.) | X
Generator Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for new generator pad (and fuel tank pad if necessary) | X
Have an architectural firm develop site compound plot drawings of compound showing tower, shelter, new generator (and fuel tank if necessary) | X
Complete one set of forms/applications to support zoning permits and approvals | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Prepare and submit construction permits for new generator (and fuel tank if necessary) | X
Prepare and submit electrical permits | X
Grade land, construct silt fences, and remove weeds and brush | X
Construct/pour generator pads (and fuel tank pad if necessary) | X
Transport, off-load, and set new generator on pad (and fuel tank if necessary) | X
Install ATS | X
Trench in generator electrical service and control circuits to shelter-mounted ATS | X
Ground generator (and fuel tank if necessary) to tower/shelter ground system | X
Fill generator fuel tank (first fill) | X
Provide factory generator technician for first-start service | X

## Site 9
Site 9 - (Insert Site Name)
Site Tasks | Contractor Name | NRVECRA | Notes
Complete one set of forms/applications to support zoning permits and approval for site changes | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Perform physical path surveys for each microwave path (microwave path studies are not final until a physical survey is made) | X
Provide existing site plans (if available) |  | X
Conduct grounding inspection and provide recommendations | X
Conduct site survey(s) and provide recommendations | X
Tower Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for tower (if new tower) | X
Grade land, construct silt fences, and remove weeds and brush | X
After assurances have been made that this site can be developed, develop site plot drawings of compound showing new tower, shelter, generator, and fuel tank locations | X
Perform geotechnical investigation for tower leg foundations in accordance with TIA-222 standards for new towers, and review results with at DDR | X
If geotechnical investigation results indicate a foundation design is required to address other than typical soil conditions. Submit a site-specific foundation design, and pricing change request, at, or prior too, DDR | X
Prepare new tower NEPA/SHPO environmental studies and THPO filings | X
Prepare and submit construction permits for new tower | X
Prepare and submit electrical permits | X
Identify specific tower attachment points to mount new antennas per the system design | X
Confirm availability of tower attachment points for proposed antennas | X
Perform tower mapping and structural analysis on existing tower and provide results at DDR. If tower fails load analysis, Contractor will provide quotes to strengthen tower (if possible), replace the tower, or provide site acquisition services. | X
Strengthen or replace tower (if required by structural analysis results) at an agreed upon additional cost and schedule adjustment | X
Provide space on existing tower to mount new system antennas at Contractor specified locations as part of the site lease(s) |  | X
Provide adequate space on cable ice bridge, and tower cable ladders, to support new cable runs | X
Install new antenna(s) using appropriate side arms and mounting hardware | X
Install antenna coax, connectors and jumpers, using cable clamps to properly secure cable to tower, and add grounding kits at the top, bottom, and on ice bridge | X
Install new tower top amplifiers for the P25 radio system | X
Install antenna lightning protection devices on each transmission line LMR run after it enters shelter via cable entry port; ground device to main ground bus bars | X
If required, install new microwave dish(es), on pipe mounts with anti-sway kits | X
Install ice shields over microwave dishes if not at the top of tower | X
Install new microwave waveguide or coaxial feed lines, secure to cable ladder(s), and add grounding kits at the top, bottom, and on ice bridge | X
Tag and identify each new antenna line | X
Sweep test each new antenna line in accordance with Contractor's “Transmission Line Analysis (Antenna Sweep) procedure | X
Shelter Tasks | Contractor Name | NRVECRA | Notes
Provide and install new shelter | X
Grade land, construct silt fences, and remove weeds and brush | X
Provide floor space in existing RF shelter for new equipment racks and DC battery plant or UPS used in the new design |  | X
Provide adequate shelter/equipment room utility AC electrical power, single-point ground system, and HVAC | X
Provide new cable entry port(s) if required | X
Upgrade existing interior ground system | X
Provide additional cable ladder for new equipment row | X
If needed, prepare and submit electrical permits on behalf of the customer | X
Install new DC power plant or UPS and wire to racks | X
Provide demarcation blocks for connection to existing legacy radios to be used in interoperability system | X
Connect site alarms to alarm punchblock (i.e smoke detector, generator, ATS, Temperature, etc.) | X
Generator Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for new generator pad (and fuel tank pad if necessary) | X
Have an architectural firm develop site compound plot drawings of compound showing tower, shelter, new generator (and fuel tank if necessary) | X
Complete one set of forms/applications to support zoning permits and approvals | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Prepare and submit construction permits for new generator (and fuel tank if necessary) | X
Prepare and submit electrical permits | X
Grade land, construct silt fences, and remove weeds and brush | X
Construct/pour generator pads (and fuel tank pad if necessary) | X
Transport, off-load, and set new generator on pad (and fuel tank if necessary) | X
Install ATS | X
Trench in generator electrical service and control circuits to shelter-mounted ATS | X
Ground generator (and fuel tank if necessary) to tower/shelter ground system | X
Fill generator fuel tank (first fill) | X
Provide factory generator technician for first-start service | X

## Site 10
Site 10 - (Insert Site Name)
Site Tasks | Contractor Name | NRVECRA | Notes
Complete one set of forms/applications to support zoning permits and approval for site changes | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Perform physical path surveys for each microwave path (microwave path studies are not final until a physical survey is made) | X
Provide existing site plans (if available) |  | X
Conduct grounding inspection and provide recommendations | X
Conduct site survey(s) and provide recommendations | X
Tower Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for tower (if new tower) | X
Grade land, construct silt fences, and remove weeds and brush | X
After assurances have been made that this site can be developed, develop site plot drawings of compound showing new tower, shelter, generator, and fuel tank locations | X
Perform geotechnical investigation for tower leg foundations in accordance with TIA-222 standards for new towers, and review results with at DDR | X
If geotechnical investigation results indicate a foundation design is required to address other than typical soil conditions. Submit a site-specific foundation design, and pricing change request, at, or prior too, DDR | X
Prepare new tower NEPA/SHPO environmental studies and THPO filings | X
Prepare and submit construction permits for new tower | X
Prepare and submit electrical permits | X
Identify specific tower attachment points to mount new antennas per the system design | X
Confirm availability of tower attachment points for proposed antennas | X
Perform tower mapping and structural analysis on existing tower and provide results at DDR. If tower fails load analysis, Contractor will provide quotes to strengthen tower (if possible), replace the tower, or provide site acquisition services. | X
Strengthen or replace tower (if required by structural analysis results) at an agreed upon additional cost and schedule adjustment | X
Provide space on existing tower to mount new system antennas at Contractor specified locations as part of the site lease(s) |  | X
Provide adequate space on cable ice bridge, and tower cable ladders, to support new cable runs | X
Install new antenna(s) using appropriate side arms and mounting hardware | X
Install antenna coax, connectors and jumpers, using cable clamps to properly secure cable to tower, and add grounding kits at the top, bottom, and on ice bridge | X
Install new tower top amplifiers for the P25 radio system | X
Install antenna lightning protection devices on each transmission line LMR run after it enters shelter via cable entry port; ground device to main ground bus bars | X
If required, install new microwave dish(es), on pipe mounts with anti-sway kits | X
Install ice shields over microwave dishes if not at the top of tower | X
Install new microwave waveguide or coaxial feed lines, secure to cable ladder(s), and add grounding kits at the top, bottom, and on ice bridge | X
Tag and identify each new antenna line | X
Sweep test each new antenna line in accordance with Contractor's “Transmission Line Analysis (Antenna Sweep) procedure | X
Shelter Tasks | Contractor Name | NRVECRA | Notes
Provide and install new shelter | X
Grade land, construct silt fences, and remove weeds and brush | X
Provide floor space in existing RF shelter for new equipment racks and DC battery plant or UPS used in the new design |  | X
Provide adequate shelter/equipment room utility AC electrical power, single-point ground system, and HVAC | X
Provide new cable entry port(s) if required | X
Upgrade existing interior ground system | X
Provide additional cable ladder for new equipment row | X
If needed, prepare and submit electrical permits on behalf of the customer | X
Install new DC power plant or UPS and wire to racks | X
Provide demarcation blocks for connection to existing legacy radios to be used in interoperability system | X
Connect site alarms to alarm punchblock (i.e smoke detector, generator, ATS, Temperature, etc.) | X
Generator Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for new generator pad (and fuel tank pad if necessary) | X
Have an architectural firm develop site compound plot drawings of compound showing tower, shelter, new generator (and fuel tank if necessary) | X
Complete one set of forms/applications to support zoning permits and approvals | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Prepare and submit construction permits for new generator (and fuel tank if necessary) | X
Prepare and submit electrical permits | X
Grade land, construct silt fences, and remove weeds and brush | X
Construct/pour generator pads (and fuel tank pad if necessary) | X
Transport, off-load, and set new generator on pad (and fuel tank if necessary) | X
Install ATS | X
Trench in generator electrical service and control circuits to shelter-mounted ATS | X
Ground generator (and fuel tank if necessary) to tower/shelter ground system | X
Fill generator fuel tank (first fill) | X
Provide factory generator technician for first-start service | X

## Site 11
Site 11 - (Insert Site Name)
Site Tasks | Contractor Name | NRVECRA | Notes
Complete one set of forms/applications to support zoning permits and approval for site changes | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Perform physical path surveys for each microwave path (microwave path studies are not final until a physical survey is made) | X
Provide existing site plans (if available) |  | X
Conduct grounding inspection and provide recommendations | X
Conduct site survey(s) and provide recommendations | X
Tower Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for tower (if new tower) | X
Grade land, construct silt fences, and remove weeds and brush | X
After assurances have been made that this site can be developed, develop site plot drawings of compound showing new tower, shelter, generator, and fuel tank locations | X
Perform geotechnical investigation for tower leg foundations in accordance with TIA-222 standards for new towers, and review results with at DDR | X
If geotechnical investigation results indicate a foundation design is required to address other than typical soil conditions. Submit a site-specific foundation design, and pricing change request, at, or prior too, DDR | X
Prepare new tower NEPA/SHPO environmental studies and THPO filings | X
Prepare and submit construction permits for new tower | X
Prepare and submit electrical permits | X
Identify specific tower attachment points to mount new antennas per the system design | X
Confirm availability of tower attachment points for proposed antennas | X
Perform tower mapping and structural analysis on existing tower and provide results at DDR. If tower fails load analysis, Contractor will provide quotes to strengthen tower (if possible), replace the tower, or provide site acquisition services. | X
Strengthen or replace tower (if required by structural analysis results) at an agreed upon additional cost and schedule adjustment | X
Provide space on existing tower to mount new system antennas at Contractor specified locations as part of the site lease(s) |  | X
Provide adequate space on cable ice bridge, and tower cable ladders, to support new cable runs | X
Install new antenna(s) using appropriate side arms and mounting hardware | X
Install antenna coax, connectors and jumpers, using cable clamps to properly secure cable to tower, and add grounding kits at the top, bottom, and on ice bridge | X
Install new tower top amplifiers for the P25 radio system | X
Install antenna lightning protection devices on each transmission line LMR run after it enters shelter via cable entry port; ground device to main ground bus bars | X
If required, install new microwave dish(es), on pipe mounts with anti-sway kits | X
Install ice shields over microwave dishes if not at the top of tower | X
Install new microwave waveguide or coaxial feed lines, secure to cable ladder(s), and add grounding kits at the top, bottom, and on ice bridge | X
Tag and identify each new antenna line | X
Sweep test each new antenna line in accordance with Contractor's “Transmission Line Analysis (Antenna Sweep) procedure | X
Shelter Tasks | Contractor Name | NRVECRA | Notes
Provide and install new shelter | X
Grade land, construct silt fences, and remove weeds and brush | X
Provide floor space in existing RF shelter for new equipment racks and DC battery plant or UPS used in the new design |  | X
Provide adequate shelter/equipment room utility AC electrical power, single-point ground system, and HVAC | X
Provide new cable entry port(s) if required | X
Upgrade existing interior ground system | X
Provide additional cable ladder for new equipment row | X
If needed, prepare and submit electrical permits on behalf of the customer | X
Install new DC power plant or UPS and wire to racks | X
Provide demarcation blocks for connection to existing legacy radios to be used in interoperability system | X
Connect site alarms to alarm punchblock (i.e smoke detector, generator, ATS, Temperature, etc.) | X
Generator Tasks | Contractor Name | NRVECRA | Notes
Stake out the desired location for new generator pad (and fuel tank pad if necessary) | X
Have an architectural firm develop site compound plot drawings of compound showing tower, shelter, new generator (and fuel tank if necessary) | X
Complete one set of forms/applications to support zoning permits and approvals | X
Sign and submit forms/applications to support zoning permits and approvals for site changes. |  | X
Prepare and submit construction permits for new generator (and fuel tank if necessary) | X
Prepare and submit electrical permits | X
Grade land, construct silt fences, and remove weeds and brush | X
Construct/pour generator pads (and fuel tank pad if necessary) | X
Transport, off-load, and set new generator on pad (and fuel tank if necessary) | X
Install ATS | X
Trench in generator electrical service and control circuits to shelter-mounted ATS | X
Ground generator (and fuel tank if necessary) to tower/shelter ground system | X
Fill generator fuel tank (first fill) | X
Provide factory generator technician for first-start service | X

## System Integration & Staging
Radio System Integration and Staging
Tasks | Contractor Name | NRVECRA | Notes
Draft Radio Staging Acceptance Test Plans as part of the DDR package | X
Approve Radio Staging Acceptance Test Plans (30 days prior to test) |  | X
Insert equipment delivery dates into the material planning system | X
Place equipment orders upon DDR approval | X
Manufacture all infrastructure equipment | X
Assemble equipment in Radio staging area(s) on a per site basis (tests may occur at different times and at different physical locations) | X
Perform Radio Staging configuration and pre-test | X
Provide appropriate personnel to participate in/witness the Radio staging acceptance tests |  | X
Perform the Radio staging acceptance tests | X | X
Provide Radio stage acceptance tests results (within 10 of each test completion) | X
Review and approve the Radio staging test results (within 10 days of completion of each test) |  | X
Provide written approval of all equipment shipments as part of staging test approval |  | X
Microwave System Integration and Staging
Tasks | Contractor Name | NRVECRA | Notes
Draft Microwave Staging Acceptance Test Plans as part of the DDR package | X
Approve Microwave Staging Acceptance Test Plans (30 days prior to test) |  | X
Insert equipment delivery dates into the material planning system | X
Place equipment orders upon DDR approval | X
Manufacture all infrastructure equipment | X
Assemble equipment in Microwave staging area(s) on a per site basis (tests may occur at different times and at different physical locations) | X
Provide appropriate personnel to participate in/witness the Microwave staging acceptance tests |  | X
Perform Microwave Staging configuration and pre-test | X
Perform the Microwave staging acceptance tests | X | X
Provide Microwave stage acceptance tests results (within 10 days of each test completion) | X
Review and approve the Microwave staging test results (within 10 days of completion of each test) |  | X
Provide written approval of all equipment shipments as part of staging test approval |  | X

## Shipping and Inventory
Infrastructure Shipping and Inventory
Tasks | Contractor Name | NRVECRA | Notes
Break down equipment and ship to sites or secure storage facility | X
Provide and pay for secure temporary storage facility | X
Provide detailed Inventory for all shipped equipment | X
Confirm detailed inventory for all delivered equipment at storage facility | X
Sort equipment in preparation for site delivery and installation | X

## System Infrastructure Install
System Infrastructure Installation
System Infrastructure Installation Tasks | Contractor Name | NRVECRA | Notes
Deliver equipment to each site | X
Install equipment, connect to ground system and apply power | X
Connect all RF cables | X
Connect all P25 system alarms | X
Interface to network, verify network connectivity | X
Dispatch Center Installation Tasks | Contractor Name | NRVECRA | Notes
Deliver equipment to each site | X
Install Consoles and Ground all Equipment | X
Install Routers | X
Install Cabling | X
Install Control Stations and Grounding | X
Install Control Stations Antennas and Grounding | X
Install/Configure Radio Gateways | X
Install Network Management Terminal(s) | X
Perform Initial Tests | X
Upgrade/Install New Logging Recorder | X
Connect Logging Recorder to Radio System, Phone Lines, etc. | X
Procure CAD vendor services to upgrade the existing CAD system to be compatible with the GPS location data, if the GPS services option is exercised | X

## Connect Network Install
Connectivty Network Infrastructure Installation
System Infrastructure Installation Tasks | Contractor | NRVECRA | Notes
Deliver equipment to each site | X
Install equipment, connect to ground system and apply power | X
Install MW Antennas and connect to ground system | X
Install Ice Shields over MW antennas | X
Install/configure microwave dehydrator | X
Install/configure Fiber interface equipment | X
Connect waveguide | X
Interface to radio system, verify network connectivity | X
Connect all alarm to Connectivity Network NMS | X
Integrate to Radio System NMS | X
Install Routers | X
Install Cabling | X
Perform Initial Tests | X

## System Optimization
System Optimization
Tasks | Contractor Name | NRVECRA | Notes
Prepare all installed sites for site inspections | X
Verify microwave/backhaul system is functional and meets reliability specifications | X
Provide frequencies to use for optimization and testing for the paging system |  | X
Verify P25 system levels and parameters are set | X
Verify P25 system alarm and network management system are operational | X
Verify system database is installed and operating correctly | X
Verify proper console configuration/operation | X
Verify proper P25 system functional operation | X
Verify proper network switching operation | X
Verify proper interoperability from gateways | X
Provide system optimization data/report | X

## Field Acceptance Testing
Field Acceptance Testing
Tasks | Contractor Name | NRVECRA | Notes
Provide appropriate team members to participate in all acceptance tests | X
Inspect each site (tower sites, dispatch centers, equipment rooms. etc), noting discrepancies on a punch list |  | X
Submit site inspection punchlist (within 15 days of site inspections) |  | X
Remedy or provide resolution plan for site inspection punchlist items (within 15 days of punchlist received) | X
Approve site inspection punchlist remedies or resolution plans (within 10 days) |  | X
Revise Acceptance Test Plans (not less than 40 days prior to beginning of each test): 1. Microwave/Connectivity Network 2. Radio System 3. BER and Signal Strength (for information only) 4. DAQ Voice Quality Coverage Acceptance (identified service areas) 5. 30-day Operational | X | X
Approve Acceptance Test Plans (within 10 days of each Test Plan submission): 1. Microwave/Connectivity Network 2. Radio System 3. BER and Signal Strength (for information only) 4. DAQ Voice Quality Coverage Acceptance (identified service areas) 5. 30-day Operational |  | X
Perform Field Acceptance Tests (notice must be given 10 days prior to beginning of each test): 1. Microwave/Connectivity Network 2. Radio System 3. BER and Signal Strength (for information only) 4. DAQ Voice Quality Coverage Acceptance (identified service areas) 5. 30-day Operational | X
Witness/Participate in Acceptance Tests: (notice must be given 30 days prior to beginning of each test): 1. Microwave/Connectivity Network 2. Radio System 3. BER and Signal Strength (for information only) 4. DAQ Voice Quality Coverage Acceptance (identified service areas) 5. 30-day Operational |  | X
Submit Acceptance Test results (within 15 days of each test completion): 1. Microwave/Connectivity Network 2. Radio System 3. BER and Signal Strength (for information only) 4. DAQ Voice Quality Coverage Acceptance (identified service areas) 5. 30-day Operational | X
Approve Acceptance Test results (within 10 days of each report submission): 1. Microwave/Connectivity Network 2. Radio System 3. BER and Signal Strength (for information only) 4. DAQ Voice Quality Coverage Acceptance (identified service areas) 5. 30-day Operational |  | X
DAQ Voice Quality Coverage Acceptance Testing Tasks | Contractor Name | NRVECRA | Notes
Provide test vehicles, and drivers for DAQ Voice Quality Coverage Acceptance Test (identified service areas) |  | X
Provide test radios for DAQ Voice Quality Coverage Acceptance Test (identified service areas) | X
Install DAQ Voice Quality Test equipment in testing vehicles | X
Provide & connect attenuators for test radios for DAQ Voice Quality Coverage Acceptance Test (identified service areas) | X
Perform Pre-test validation of DAQ Voice Quality Test Configuration | X | X
Perform DAQ Voice Quality Acceptance Testing | X | X
Retry DAQ Voice Quality test for failed test tiles as defined in the mutually agree upon Acceptance Test Plans. Contractor will coordinate with NRVECRA representatives to be present during the retest. | X | X

## Terminal Equipment
Terminal Equipment
Shipping and Inventory Tasks | Contractor Name | NRVECRA | Notes
Order terminal equipment (mobiles/portables/pagers/control stations) after receipt of NRVECRA written approval | X
Survey control station installation locations | X
Provide written authorization to ship terminal equipment |  | X
Provide detailed Inventory of terminal equipment (mobiles/portables/pagers/control stations, and subscriber accesories) | X
Deliver terminal equipment (mobiles/portables/pagers/control stations, and subscriber accesories) after receipt of NRVECRA written approval | X
Confirm detailed inventory for delivered terminal equipment (mobiles/portables/pagers/control stations, and subscriber accesories) | X
Control Station Radio Tasks | Contractor Name | NRVECRA | Notes
Provide access to control station installation locations to meet the project schedule timeline |  | X
Program and install control stations and control station antennas | X
Provide pre and post control station installation assessments, presenting installation documentation for customer acceptance for each control station location. | X
Provide a representative to review control station installation documentation and provide acceptance for each location |  | X
Mobile Radio Tasks | Contractor Name | NRVECRA | Notes
Provide a central facility for mobile vehicle installation |  | X
Provide vehicles for mobile installation to meet the project schedule timeline |  | X
Program and install mobile units | X
Perform pre and post testing of emergency vehicle systems (Sirens, Lights, MDT's, GPS, etc) | X
Provide pre and post installation vehicle assessments, presenting installation documentation for customer acceptance for each vehicle | X
Provide a representative to review installation documentation and provide acceptance for each vehicle |  | X
Portable Radio and Pager Tasks | Contractor Name | NRVECRA | Notes
Program and distribute portable units with accessories | X | X
Program and distribute pager units | X

## Training, Fleetmapping, Cutover
Training, Fleetmapping, and Cutover
Training Tasks | Contractor Name | NRVECRA | Notes
Develop training plan and schedule (collaborative effort) | X | X
Identify system administrators |  | X
Provide system administrator training | X
Attend system administrator training |  | X
Identify system maintenance technicians |  | X
Provide radio system maintenance training | X
Attend radio system maintenance training |  | X
Provide connectivity network maintenance training | X
Attend connectivty network maintenance training |  | X
Provide radio user training | X
Attend radio user training (including Public Safety Telecommunicators) |  | X
Identify radio user trainers |  | X
Provide radio user train-the-trainer training | X
Attend radio user train-the-trainer training |  | X
Provide console training (including backup control station training) | X
Attend console training |  | X
Identify console trainers |  | X
Provide console train-the-trainer training | X
Attend console train-the-trainer training |  | X
Provide training on upgraded/new Logging Recorder | X
Attend training on upgraded/new Logging Recorder |  | X
Fleetmapping Tasks | Contractor Name | NRVECRA | Notes
Provide online/remote system fundaments training | X
Provide workshops for talk-group planning | X
Attend workshop for talk-group planning |  | X
Develop user programming profiles (collaborative effort) | X | X
Develop console programming profiles (collaborative effort) | X | X
Develop and enter system database | X
Cutover Tasks | Contractor Name | NRVECRA | Notes
Define which interoperability channels are desired during cutover |  | X
Create interoperability channels for cutover, using proposed gateways | X
Agree to cutover date, time, and all necessary participants |  | X
Revise Draft Cutover Plan (not less than 40 days prior to beginning cutover) | X
Review & Approve cutover plan (not less than 30 days prior to beginning cutover) |  | X
Notify users of system cutover date |  | X
Schedule all required subcontractors needed for cutover | X
Proceed with system cutover according to cutover plan | X | X
Submit letter of conditional system acceptance within 5 days following cutover | X
Approve conditional system acceptance and sign letter within 10 days of completion of a successful cutover |  | X

## Final Acceptance
Final Acceptance
Tasks | Contractor Name | NRVECRA | Notes
Removal of decommissioned legacy network, console, or site infrastructure equipment | X
Submit draft as-built documentation package (15 days prior to submission of final acceptance letter) | X
Review/Comment on draft as-built and maintenance documentation package (within 15 days) |  | X
Submit final drawing as-built and maintenance documentation package (within 15 days) | X
Submit letter of final system acceptance | X
Provide warranty and maintenance contact information | X
Meet with CONTRACTOR to outline warranty/maintenance contact procedures |  | X
Outline system support and services requirements | X | X
Accept final drawings, as-built, and maintenance documentation package (within 15 days) |  | X
Sign letter of final system acceptance (within 10 days of receipt of letter) |  | X